## Controls
Last reviewed by the ISMS committee on 2026-09-30. Do not sort.
Control ID | Control | Details | Category | CSF Function | Status | Priority | Effort | Owner | Due date | Evidence link
ISMS-01 | Information security policy | Approve and publish the top-level policy | Policy | Govern | Done | High | S | ciso@acme.com | 2026-03-31 | https://intranet.acme.com/isms/policy
ISMS-02 | MFA for remote access | Enforce MFA on VPN and webmail | Technical | Protect | In Progress | High | M | it.ops@acme.com | 2026-12-15
ISMS-03 | Quarterly access review | Review privileged accounts every quarter | Process | Identify | Planned | Medium | M | iam@acme.com | Q1 2027
ISMS-04 | EDR on all endpoints | Roll out the EDR agent fleet-wide | Technical | Detect | In Progress | P1 | Large | soc@acme.com | 2026-11-30
ISMS-05 | Backup restore tests | Restore a sample every month | Procedure | Recover | On hold | Medium | S | it.ops@acme.com | 2026-10-31
ISMS-06 | Security awareness training | Annual training and phishing drills | Process | Protect | Done | Low | M | hr@acme.com | 2026-06-30 | https://lms.acme.com/sec101
ISMS-07 | Incident response plan | Write and test the IR playbooks | Policy | Respond | Not started | High | L | soc@acme.com | 2027-01-31
ISMS-08 | Badge access to server rooms | Restrict and log physical access | Physical | Protect | Done | Medium | XS | facilities@acme.com | 2026-02-28
ISMS-09 | Vulnerability scanning | Weekly authenticated scans | Technical | Identify | Deprecated | Low | S | soc@acme.com
ISMS-10 | Supplier security clauses | Add security annex to contracts | Process | Govern | In progress | Medium | M | legal@acme.com | 2026-12-31